## Sprint 1
Amigo Sprint 1 | Dates: | 04/01/19 - 04/12/19 |  | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Done | 11156 |  | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 5 | 5 | 0
| 11137 |  | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
|  | 11185 | 16 | 16 | 16 | 16 | 8 | 8 | 12 | 12 | 12 | 12 | 2
Completed |  | 11186 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0
|  | 11187 | 8 | 8 | 8 | 8 | 8 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 3.5
Completed |  | 11188 | 0 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11189 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
| 11136 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11172 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Completed |  | 11173 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11174 | 6 | 6 | 6 | 6 | 4 | 4 | 8 | 8 | 8 | 8 | 7.9
|  | 11175 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 11077 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11176 | 1 | 1 | 1 | 0 | 8 | 6 | 6 | 6 | 6 | 6 | 6
Completed |  | 11192 | 0 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Demo | 11078 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completed |  | 11178 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 0.5 | 0
Completed |  | 11193 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11079 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11177 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3
|  | 11261 | 0 | 4 | 4 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| 11080 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11084 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | 11091 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6
|  | 11179 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | 11180 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | 11181 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | 11182 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | 11183 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12
|  | 11184 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| 11083 |  | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | 11190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11098 |  | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | 11191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - Remaining task hours |  |  | 210 | 189 | 168 | 147 | 126 | 105 | 84 | 63 | 42 | 21 | 0
Actual - Remaining task hours |  |  | 210 | 215.25 | 217.25 | 215.75 | 200.5 | 197 | 199 | 196.5 | 179.5 | 179 | 148.4

## ITR14
ITR 14 | Dates: | 04/15/19 - 04/26/19 |  | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
| 11578 |  | 48 | 48 | 48 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11581 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 18 | 12 | 6 | 0
| Added | 11647 |  | 2019-04-17: 0; 2019-04-23: 0; 2019-04-24: 0; 2019-04-25: 0; 2019-04-26: 0
| 11137 |  | 48 | 48 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11187 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 0
|  | 11188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11189 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 10 | 10
| 11136 |  | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11172 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  | 11173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11174 | 8 | 8 | 8 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | 11175 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2
| 11383 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 4 | 4
| 11082 |  | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 10 | 7 | 7
| Added | 11648 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Added | 11670 |  | 2019-04-22: 0; 2019-04-23: 0; 2019-04-24: 0; 2019-04-25: 0; 2019-04-26: 0
11079
|  | 11177 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0.25 | 0.25
|  | 11261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11384 |  | 24 | 22 | 17 | 22 | 22 | 22 | 22 | 22 | 22 | 0 | 0
Removed | 11558 |  | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 16 | 12 | 0 | 0
Ideal - Remaining task hours |  |  | 269.5 | 242.55 | 215.6 | 188.65 | 161.7 | 134.75 | 107.8 | 80.85 | 53.9 | 26.95 | 0
Actual - Remaining task hours |  |  | 269.5 | 267.5 | 262.5 | 257.5 | 232.5 | 173.5 | 173.5 | 179.5 | 131.5 | 37.75 | 26.25

## ITR15
ITR15 | Dates: | 05/08/19 - 05/21/19 |  | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-20 | 2019-05-21
Status | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
In Development | 11137 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Complete |  | 11186 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Complete |  | 11187 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Complete |  | 11188 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
In Progress |  | 12012 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2
| 12075 |  | 30 | 28 | 28 | 28 | 26 | 26 |  | 10 | 10 | 10
|  | 12496 |  | 2019-05-16: 0; 2019-05-17: 0; 2019-05-20: 0
| 11867 |  | 10 | 8 | 8 | 6 | 6 | 4 | 2 | 0 | 0 | 0
| 12041 |  | 19 | 18 | 18 | 16 | 16 | 16 | 16 | 16 | 16 | 16
| 11189 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| 12042 |  | 80 | 80 | 72 | 64 | 56 | 48 | 16 | 16 | 16 | 8
|  | 12043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Complete |  | 12088 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 12428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 12076 |  | 10 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
|  | 12084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11998 |  | 40 | 35 | 35 | 30 | 30 | 22 | 22 | 14 | 14 | 14
| 12077 |  | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0
| 12078 |  | 40 | 35 | 35 | 35 | 35 | 21 | 15 | 9 | 9 | 9
| 12079 |  | 40 | 35 | 30 | 30 | 30 | 30 | 24 | 18 | 18 | 18
| 11991 |  | 32 | 32 | 32 | 32 | 32 | 26 | 0 | 0 | 0 | 0
|  | 12358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 11994 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 8 | 0 | 0
| 12044 |  | 60 | 55 | 49 | 45 | 40 | 34 | 28 | 24 | 24 | 18
| 12099 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Needs Estimate |  | 12046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Needs Estimate |  | 12047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12045 |  | 60 | 54 | 48 | 44 | 38 | 32 | 26 | 20 | 20 | 14
| 12048 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| 12050 |  | 60 | 60 | 60 | 60 | 60 | 60 | 44 | 44 | 44 | 38
| 11383 |  | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 0
| 12226 |  | 40 | 35 | 30 | 30 | 30 | 30 | 22 | 22 | 22 | 0
|  | 12495 |  | 2019-05-15: 0; 2019-05-16: 0; 2019-05-17: 0; 2019-05-20: 0
| 11079 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11177 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
Complete |  | 11261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12087 |  | 8 | 5 | 5 | 5 | 3 | 2 | 1 | 1 | 1 | 1
| 12085 |  | 12 | 12 | 12 | 10 | 8 | 8 | 8 | 8 | 8 | 8
Blocked | 11384 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Complete |  | 11649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Complete |  | 11650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Complete |  | 11651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Complete |  | 11667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11668 | 0 | 2019-05-08: 0; 2019-05-09: 0; 2019-05-10: 0; 2019-05-13: 0; 2019-05-14: 0
Complete |  | 11682 |  | 2019-05-13: 0; 2019-05-14: 0; 2019-05-15: 0
Ideal - Remaining task hours |  |  | 582.25 | 524.025 | 465.8 | 407.575 | 349.35 | 291.125 | 232.9 | 174.675 | 116.45 | 58.225 | 0
Actual - Remaining task hours |  |  | 582.25 | 537.25 | 507.25 | 480.25 | 453.25 | 400.25 | 245.25 | 228.25 | 220.25 | 170.25

## ITR16
ITR16 | Dates: | 05/22/19 - 06/04/19 |  | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-03 | 2019-06-04
Status | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
| 12041 |  | 16 | 16 | 16 | 14 | 14 | 14 | 14 | 14 | 12 | 12 | 12
| 11382 |  | 8 | 8 | 8 | 7 | 7 | 5 | 5 | 2 | 0 | 0 | 0
| 11385 |  | 8 | 8 | 8 | 7 | 7 | 5 | 5 | 2 | 0 | 0 | 0
| 11386 |  | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 5 | 0 | 0 | 0
| 12087 |  | 4 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 12085 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 2 | 2 | 2
| 12074 |  | 30 | 30 | 30 | 30 | 30 | 30 | 15 | 15 | 9 | 9 | 0
|  | 12743 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 12036 |  | 80 | 80 | 40 | 36 | 36 | 36 | 24 | 18 | 18 | 5 | 0
|  | 12038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12037 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12004 |  | 40 | 40 | 40 | 52 | 52 | 52 | 42 | 36 | 12 | 3.5 | 0
| 12022 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 11993 | Removed | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| 11992 |  | 40 | 40 | 36 | 32 | 32 | 32 | 32 | 32 | 12 | 12 | 0
| 12496 |  | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
| 12557 |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 14 | 0
| 12558 |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 20 | 16
| 12560 |  | 24 | 24 | 24 | 18 | 18 | 14 | 14 | 9 | 5 | 5 | 16
|  | 12561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completed | 11080 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11180 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11083 |  | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 2 | 2 | 0 | 0
| 12630 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
| 12099 |  | 32 | 32 | 29 | 25 | 25 | 19 | 13 | 7 | 0 | 0 | 0
|  | 12046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 12047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Removed |  | 11091 | 8 | 2019-05-22: 6
| 12601 | fixed => | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 1.5 | 1.5 | 1.5 | 1.5
| 12602 |  | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0
| 12603 |  | 16 | 16 | 16 | 16 | 16 | 16 | 11 | 11 | 0 | 0 | 0
| 12604 |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 21 | 21 | 21
| 12055 |  | 21 | 21 | 15 | 15 | 15 | 9 | 6 | 4 | 2 | 2 | 0
| 12045 |  | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 17 | 13 | 6 | 6
| 12605 |  | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 0
12725
12726
12727
Ideal - Remaining task hours |  |  | 565 | 508.5 | 452 | 395.5 | 339 | 282.5 | 226 | 169.5 | 113 | 56.5 | 0
Actual - Remaining task hours |  |  | 565 | 561 | 502 | 489 | 489 | 468 | 377 | 331.5 | 191.5 | 124 | 82.5

## ITR17
ITR17 | Dates:
Status | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Ideal - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual - Remaining task hours |  |  | 0 | 0 | 0 | 0

## ITR18
ITR18 | Dates:
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Ideal - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 7
Sprint 1 | Dates:
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
My Project | Story 1 | Task 1.1
My Project | Story 1 | Task 1.2
My Project | Story 1 | Task 1.3
My Project | Story 2 | Task 2.1
My Project | Story 2 | Task 2.2
My Project | Story 3 | Task 3.1
My Project | Story 3 | Task 3.2
My Project | Story 3 | Task 3.3
My Project | Story 3 | Task 3.4
My Project | Story 4 | Task 4.1
My Project | Story 4 | Task 4.2
My Project | Story 4 | Task 4.3
My Project | Story 4 | Task 4.4
Ideal - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 8
Sprint 1 | Dates:
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
My Project | Story 1 | Task 1.1
My Project | Story 1 | Task 1.2
My Project | Story 1 | Task 1.3
My Project | Story 2 | Task 2.1
My Project | Story 2 | Task 2.2
My Project | Story 3 | Task 3.1
My Project | Story 3 | Task 3.2
My Project | Story 3 | Task 3.3
My Project | Story 3 | Task 3.4
My Project | Story 4 | Task 4.1
My Project | Story 4 | Task 4.2
My Project | Story 4 | Task 4.3
My Project | Story 4 | Task 4.4
Ideal - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 9
Sprint 1 | Dates:
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
My Project | Story 1 | Task 1.1
My Project | Story 1 | Task 1.2
My Project | Story 1 | Task 1.3
My Project | Story 2 | Task 2.1
My Project | Story 2 | Task 2.2
My Project | Story 3 | Task 3.1
My Project | Story 3 | Task 3.2
My Project | Story 3 | Task 3.3
My Project | Story 3 | Task 3.4
My Project | Story 4 | Task 4.1
My Project | Story 4 | Task 4.2
My Project | Story 4 | Task 4.3
My Project | Story 4 | Task 4.4
Ideal - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 10
Sprint 1 | Dates:
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
My Project | Story 1 | Task 1.1
My Project | Story 1 | Task 1.2
My Project | Story 1 | Task 1.3
My Project | Story 2 | Task 2.1
My Project | Story 2 | Task 2.2
My Project | Story 3 | Task 3.1
My Project | Story 3 | Task 3.2
My Project | Story 3 | Task 3.3
My Project | Story 3 | Task 3.4
My Project | Story 4 | Task 4.1
My Project | Story 4 | Task 4.2
My Project | Story 4 | Task 4.3
My Project | Story 4 | Task 4.4
Ideal - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 11
Sprint 1 | Dates:
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
My Project | Story 1 | Task 1.1
My Project | Story 1 | Task 1.2
My Project | Story 1 | Task 1.3
My Project | Story 2 | Task 2.1
My Project | Story 2 | Task 2.2
My Project | Story 3 | Task 3.1
My Project | Story 3 | Task 3.2
My Project | Story 3 | Task 3.3
My Project | Story 3 | Task 3.4
My Project | Story 4 | Task 4.1
My Project | Story 4 | Task 4.2
My Project | Story 4 | Task 4.3
My Project | Story 4 | Task 4.4
Ideal - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 12
Sprint 1 | Dates:
Project | Story | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
My Project | Story 1 | Task 1.1
My Project | Story 1 | Task 1.2
My Project | Story 1 | Task 1.3
My Project | Story 2 | Task 2.1
My Project | Story 2 | Task 2.2
My Project | Story 3 | Task 3.1
My Project | Story 3 | Task 3.2
My Project | Story 3 | Task 3.3
My Project | Story 3 | Task 3.4
My Project | Story 4 | Task 4.1
My Project | Story 4 | Task 4.2
My Project | Story 4 | Task 4.3
My Project | Story 4 | Task 4.4
Ideal - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual - Remaining task hours |  |  | 0 | 0 | 0 | 0 | 0 | 0